{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["明细表"],"not_rendered":{"defined_names":2},"read":"whole","date_system":"1900"}

{"sheet":"明细表","index":0,"n_rows":102,"n_cols":11,"rows_kept":102,"merged":[[1,0,1,10]]}
[null,"附件1"]
["增补陆丰市乡村振兴驻镇帮镇扶村项目（巩固拓展脱贫攻坚成果同乡村振兴有效衔接）入库储备明细表"]
[]
[]
["序号","单位","计划实施年度","类型","项目名称","项目规模","项目地点","项目预算总投资（万元）","绩效目标","实施单位名称","备注"]
[1,"陆丰市农业农村局","2025年","其他驻镇帮镇扶村","陆丰市2025年农产品质量安全监测项目","组织实施农产品质量安全监管工作，完成2025年定量监测样品数量2000批次，其中监督抽查抽检数量占比总批次数不低于20%。","陆丰市",200,"组织实施农产品质量安全监管工作，完成2025年定量监测样品数量2000批次，其中监督抽查抽检数量占比总批次数不低于20%。","全市各地"]
[2,"陆丰市农业农村局","2025年","其他驻镇帮镇扶村","陆丰市人环境提升及绿化项目","进一步提升农村人居环境及对村庄进行补绿","陆丰市",236,"改善农村人居环境≥100%\n提升美丽乡村绿化美化","全市各地"]
[3,"陆丰市自然资源局","2025年","开发补充耕守住粮安全","全市补充补耕地项目","开发补充耕地12306亩","全市各地",1230,"新增耕地面积356亩，耕地质量达到相关标准要求。","全市各地"]
[4,"东海街道","2025年","典型村培育","陆丰市东海街道上海村人居环境整治项目工程","包括村庄道路提升1.4公里、“四小园”建设、绿美生态建设：植树200余棵等。","上海村",150,"人居环境改善，群众满意度≧95％以上","东海街道办事处"]
[5,"东海街道","2025年","典型村培育","陆丰市东海街道深埔村集体产业生产车间项目","新建一栋两层产业生产车间，长度约28.3米，宽度约9.9米，高10.8米，总建筑面积589.86平方米，包含室外硬底化及排水等。","深埔村",130,"人居环境改善，群众满意度≧95％以上","东海街道办事处"]
[6,"东海街道","2025年","典型村培育","陆丰市东海街道头肖村（上围）人居环境整治项目","头肖上围村巷道硬底总长1719米，巷宽6米，巷道面积7113平方米，含巷道硬底化及雨水口、检查井等","头肖村",123,"人居环境改善，群众满意度≧95％以上","东海街道办事处"]
[7,"东海街道","2025年","典型村培育","陆丰市东海街道深埔村绿美建设项目","种植黄槐树约150棵","深埔村",4,"人居环境改善，群众满意度≧95％以上","东海街道办事处"]
[8,"东海街道","2025年","典型村培育","东海街道宽塘村村道巷道整治提升工程","预计实施道路整治提升1.2公里","宽塘村",120,"人居环境改善，群众满意度≧95％以上","东海街道办事处"]
[9,"东海街道","2025年","典型村培育","东海街道龙口村村道巷道整治提升工程","预计实施道路整治提升1公里","龙口村",120,"人居环境改善，群众满意度≧95％以上","东海街道办事处"]
[10,"碣石镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市碣石镇后埔村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","碣石镇后埔村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","碣石镇后埔村"]
[11,"碣石镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市碣石镇诗书社区扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","碣石镇诗书社区",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","碣石镇诗书社区"]
[12,"碣石镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市碣石镇水朝社区扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","碣石镇水朝社区",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","碣石镇水朝社区"]
[13,"碣石镇","2025年","典型村培育","陆丰市碣石镇角溪坂村村庄公园建设工程","约2000平方米及配套设施","碣石镇角溪坂村",30,"新建一个村庄公园","碣石镇角溪坂村委会"]
[14,"碣石镇","2025年","其他驻镇帮镇扶村","陆丰市碣石镇田头园村农贸市场建设工程","建设一个农贸市场，占地面积约2000平方米","碣石镇田头园村",150,"新建一个农贸市场","碣石镇田头园村委会"]
[15,"碣石镇","2025年","其他驻镇帮镇扶村","陆丰市碣石镇角溪坂村环村路建设工程","长约1.2公里，宽8米","碣石镇角溪坂村",95.47,"新建一条道路","碣石镇角溪坂村委会"]
[16,"甲子镇","2025年","典型村培育","陆丰市甲子镇第八小学前口袋公园及挡土围墙建设工程","挡土墙长90米*高4米、石质栏杆110米、花岗石石材人行道300㎡、绿化500㎡、填土方2000m³。","甲子镇东方村",62,"1、资金支出率≥95%\n2.后续管理长期落实","甲子镇东方村民委员会"]
[17,"南塘镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市南塘镇乌石村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","南塘镇乌石村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","南塘镇乌石村"]
[18,"南塘镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市南塘镇竹坑村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","南塘镇竹坑村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","南塘镇竹坑村"]
[19,"南塘镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市南塘镇龙岭村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","南塘镇龙岭村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","南塘镇龙岭村"]
[20,"南塘镇","2025年","其他驻镇帮镇扶村","南塘镇四池村后地龙道路修建项目","长度240米，宽度4.5米","四池村",30,"项目验收合格率100%，群众满意度≥95%","南塘镇四池村委会"]
[21,"南塘镇","2025年","其他驻镇帮镇扶村","南塘镇新河村人行道及池塘边升级改造工程","建设长300米、宽2米人行道和对三个池塘环池边道路长450米、宽5米进行铺设","新河村",50,"项目验收合格率100%，群众满意度≥95%","南塘镇新河村委会"]
[22,"南塘镇","2025年","典型村培育","南塘镇后西村“三清三拆三整治”项目","① “三清”：清理村巷道乱堆乱放、房前屋后垃圾杂草及沟渠池塘溪河淤泥漂浮物；  \n② “三拆”：拆除危旧房、废弃猪牛栏及露天厕所，整治乱搭乱建、违规广告牌等；  \n③“三整治”：整治垃圾乱扔、污水乱排、“三线”（电力、通信、广电）乱搭问题。 ","后西村",30,"项目验收合格率100%，群众满意度≥95%","南塘镇后西村委会"]
[23,"南塘镇","2025年","典型村培育","南塘镇汤湖村“三清三拆三整治”项目","① “三清”：清理村巷道乱堆乱放、房前屋后垃圾杂草及沟渠池塘溪河淤泥漂浮物；  \n② “三拆”：拆除危旧房、废弃猪牛栏及露天厕所，整治乱搭乱建、违规广告牌等；  \n③“三整治”：整治垃圾乱扔、污水乱排、“三线”（电力、通信、广电）乱搭问题。 ","汤湖村",30,"项目验收合格率100%，群众满意度≥95%","南塘镇汤湖村委会"]
[24,"甲西镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市甲西镇政坑村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","甲西镇政坑村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","甲西镇政坑村"]
[25,"甲西镇","2025年","典型村培育","甲西镇濠头村陆城道路硬底化建设工程","4米X700米道路硬底化",{"$f":"LEFT(E30,9)","v":"甲西镇濠头村陆城道"},40,"1、年度资金支出进度≥100%；\n2、工程验收合格率≥100%；\n3、基础设施服务基本满足群众需求；\n4、农村人居环境持续改善；\n5、群众满意度≥95%。","陆丰市甲西镇濠头村委会"]
[26,"甲西镇","2025年","其他驻镇帮镇扶村","陆丰市甲西镇新寨村石头潭至西河堤道路硬底化工程","对新寨村石头潭至西河堤道路进行硬底化，路长400米，宽5米。",{"$f":"LEFT(E31,9)","v":"陆丰市甲西镇新寨村"},40,"1、年度资金支出进度≥100%；\n2、工程验收合格率≥100%；\n3、基础设施服务基本满足群众需求；\n4、农村人居环境持续改善；\n5、群众满意度≥95%。","陆丰市甲西镇新寨村委会"]
[27,"甲西镇","2025年","其他驻镇帮镇扶村","陆丰市甲西镇新寨村地灵修善工程","新寨村地灵修整，包含清理杂草，增加路灯，硬底化道路等。",{"$f":"LEFT(E32,9)","v":"陆丰市甲西镇新寨村"},40,"1、年度资金支出进度≥100%；\n2、工程验收合格率≥100%；\n3、基础设施服务基本满足群众需求；\n4、农村人居环境持续改善；\n5、群众满意度≥95%。","陆丰市甲西镇新寨村委会"]
[28,"甲西镇","2025年","典型村培育","甲西镇新寨村新南三街路面修复工程","新寨村新南三街路面修复，路长300米，宽11米。",{"$f":"LEFT(E33,9)","v":"甲西镇新寨村新南三"},40,"1、年度资金支出进度≥100%；\n2、工程验收合格率≥100%；\n3、基础设施服务基本满足群众需求；\n4、农村人居环境持续改善；\n5、群众满意度≥95%。","陆丰市甲西镇新寨村委会"]
[29,"甲西镇","2025年","其他驻镇帮镇扶村","陆丰市甲西镇乡镇建设规划（2024-2026年）","陆丰市甲西镇乡镇建设规划（2024-2026年）","陆丰市甲西镇",70,"1、严格把控时间节点，完成规划编制；\n2、规划内容具备科学性、前瞻性和可操作性；\n3、年度资金支出进度≥100%。","陆丰市甲西镇人民政府"]
[30,"城东街道","2025年","典型村培育","东埔后村环村路建设工程项目","400米*5米道路硬底化","东埔后村环村路",30,"工程竣工验收合格率100%;资金使用不发生重大违规违纪问题；农户满意度≥90%；项目建设进度达标率（%）≥80%；完成自然村内支路硬底化数1（个）","城东街道东埔村"]
[31,"河西街道","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市河西街道山脚村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","河西街道山脚村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","河西街道山脚村"]
[32,"河西街道","2025年","典型村培育","河西街道香校村环境卫生整治和水利沟整治工程","环境卫生整治，整治水利沟3000米","河西街道香校村",30,"改善村容村貌，提升村民生活环境质量","河西街道香校村委会"]
[33,"河西街道","2025年","典型村培育","河西街道夏陇村许厝围村巷道修建工程","许厝围村巷道硬底化，九条巷道长每条120米，宽2米。","河西街道夏陇村",30,"改善村民出行条件，提升基础设施水平","河西街道夏陇村委会"]
[34,"八万镇","2025年","典型村培育","八万镇吉水村路灯、广场灯建设项目","对吉水辖区内各自然村进行照明加强，安装广场灯、路灯","八万镇吉水村",30,"1、年度建设项目开工率100%；2、年度建设任务完成率≥95%；3、受益群众满意度≥95%","八万镇吉水村民委员会"]
[35,"八万镇","2025年","典型村培育","八万镇八万村坝心村村内排污管建设项目","建设坝心村村内排污管","八万镇八万村",30,"1、年度建设项目开工率100%；2、年度建设任务完成率≥95%；3、受益群众满意度≥95%","八万镇八万村民委员会"]
[36,"八万镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市八万镇新葫村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","八万镇新葫村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","八万镇新葫村"]
[37,"八万镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市八万镇新坑村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","八万镇新坑村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","八万镇新坑村"]
[38,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇草洋村老乡面前至河边道路建设工程","约920M*4M","草洋村",85,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[39,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇草洋村学校至石将军道路建设工程","约1400M*4M","草洋村",160,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[40,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇草洋村大路百公至河仔果林坋道路建设工程","约1200M*4M","草洋村",105,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[41,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇草洋村巷道硬化建设工程","约7700M","草洋村",50,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[42,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇草洋村坑尾头农田水利灌溉渠道建设工程","约1000M","草洋村",60,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[43,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇草洋村学老坑农田水利灌溉渠道建设工程","约2500M","草洋村",120,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[44,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇草洋村塘尾岭农田水利灌溉渠道建设工程","约800M","草洋村",50,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[45,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇草洋村洋仔农田水利灌溉渠道建设工程","约800M","草洋村",50,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[46,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇莲花村饮用水源新建蓄水山塘项目工程","新建一道拦水堤坝，水坝高12米，坝顶长度50米，坝底长度8米；建一个日处理量90立方米的蓄水池；清理塘口内1万平方米植被","莲花村",226,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[47,"陂洋镇","2025年","典型村培育","洋口村至大径村道路两边水沟整治及道路路灯工程","路长1公里左右，约30盏灯","洋口村",30,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府洋口村民委员会"]
[48,"陂洋镇","2025年","典型村培育","陆丰市陂洋镇陂沟村四清桥安全防护和陂沟河斜坡硬化项目","四清桥安全护栏约120米；四清桥上下游陂沟河斜坡硬化约5000平方米","陂沟",30,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府陂沟村民委员会"]
[49,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇古寨村八村沟头雨水分流和乡村公园提升改造工程","古寨八村沟头自然村雨水分流改造；沟头和后环村头公园设施改造石块小路、铺草皮，石桌、宣传指示牌等配套设施，","古寨村",28.02,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[50,"陂洋镇","2025年","其他驻镇帮镇扶村","陂洋镇古寨村南坝引水渠道修缮工程","约长3公里渠道堵塞清泥与加固修补等配套建设","古寨村",30,"改善人居环境，提高群众满意度，守好不发生规模性返贫底线","陂洋镇人民政府"]
[51,"博美镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市博美镇蛟溪村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","博美镇蛟溪村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","博美镇蛟溪村"]
[52,"博美镇","2025年","典型村培育","博美镇溪墘村绿美公园建设工程","在溪墘村芙蓉村修缮埕地并进行绿化，打造绿美小公园。面积约1000平方。","博美镇溪墘村",30,"1、年度建设项目开工率100%；\n2、年度建设任务完成率≥95%；\n3、受益群众满意度≥95%","博美镇溪墘村民委员会"]
[53,"博美镇","2025年","典型村培育","博美镇赤坑村虎坑村组中路硬底化工程","对博美镇赤坑村虎坑村组中路路面硬底化，长度约300米。","博美镇赤坑村",30,"1、年度建设项目开工率100%；\n2、年度建设任务完成率≥95%；\n3、受益群众满意度≥95%","博美镇赤坑村民委员会"]
[54,"大安镇","2025年","典型村培育","陆丰市大安镇大安村南社河畔公园提升建设工程","铺设仿大理石砖1250㎡，增加绿化池20个并种植树木，修补路面100平方，配套自动浇水设施，石凳，健身器材等。","大安村",30,"1.(一)经济效益: 加快年度资金支出进度;（二）群众满意度: 农户满意度指标值90%以上；(三)生态效益: 改善农村人居环境，提升小公园1个。","陆丰市大安镇大安村民委员会"]
[55,"大安镇","2025年","典型村培育","陆丰市大安镇河二村楼仔绿美公园建设工程","在河二村楼仔自然村打造绿美公园，种植树木，修补公园入口道路200米，搭配桌椅等配套休闲设施。","河二村",30,"1.(一)经济效益: 加快年度资金支出进度;（二）群众满意度: 农户满意度指标值90%以上；(三)生态效益: 改善农村人居环境，建设绿美小公园1个。","陆丰市大安镇河二村民委员会"]
[56,"河东镇","2025年","典型村培育","陆丰市河东镇后坎村绿化提升项目","购买树苗、花圃等，提升村内绿化水平","河东镇后坎村",9,"群众满意度≧90%","河东镇人民政府"]
[57,"河东镇","2025年","典型村培育","陆丰市河东镇后坎村内道路提升项目","对辖区内道路进行修补提升","河东镇后坎村",18,"群众满意度≧91%","河东镇人民政府"]
[58,"河东镇","2025年","典型村培育","陆丰市河东镇后坎村体育设施项目","购买体育器材等","河东镇后坎村",3,"群众满意度≧92%","河东镇人民政府"]
[59,"湖东镇","2025年","典型村培育","湖东镇竹新村道路硬底化工程","竹新村西边路硬底化，长1公里，宽3米。","湖东镇竹新村",30,"资金支出进度：100%；\n竣工验收合格率：100%；\n群众满意度：＞95%；\n改善农村人居环境：100%","湖东镇竹新村民委员会"]
[60,"湖东镇","2025年","典型村培育","湖东镇长溪村村头公园建设工程","修建一个村头公园及配套绿化、休闲设施。","湖东镇长溪村",30,"资金支出进度：100%；\n竣工验收合格率：100%；\n群众满意度：＞95%；\n改善农村人居环境：100%","湖东镇长溪村民委员会"]
[61,"湖东镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市湖东镇竹湖村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","湖东镇竹湖村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","湖东镇竹湖村"]
[62,"湖东镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市湖东镇竹林村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","湖东镇竹林村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","湖东镇竹林村"]
[63,"甲东镇","2025年","典型村培育","陆丰市甲东镇洋美村唐厝至村委门口主干道两侧提升建设工程","唐厝村至洋美村委门口，400米道路两侧人行道建设及部分绿化工程","洋美村",30,"工程竣工验收合格率100%，受益群众满意度达95%以上。","甲东镇洋美村委会"]
[64,"甲东镇","2025年","其他驻镇帮镇扶村","陆丰市甲东镇旺厝村村头小公园建设项目","旺厝村村头公园建设400平方米","甲东镇旺厝村",20,"工程竣工验收合格率100%，受益群众满意度达95%以上。","甲东镇旺厝村委会"]
[65,"甲东镇","2025年","其他驻镇帮镇扶村","陆丰市甲东镇东林村垃圾收集点建设项目","建设12个垃圾点，改善居住环境，确保村民身心健康","甲东镇东林村",25,"工程竣工验收合格率100%，受益群众满意度达95%以上。","甲东镇人民政府"]
[66,"甲东镇","2025年","其他驻镇帮镇扶村","陆丰市甲东镇东林村老市场升级改造建设工程","升级改造村内农贸市场","甲东镇东林村",30,"工程竣工验收合格率100%，受益群众满意度达95%以上。","甲东镇人民政府"]
[67,"甲东镇","2025年","其他驻镇帮镇扶村","陆丰市甲东镇东林村六乱整治工程","东林村主次干道沿途道路及周边环境卫生整治提升","甲东镇东林村",25,"工程竣工验收合格率100%，受益群众满意度达95%以上。","甲东镇人民政府"]
[68,"甲东镇","2025年","其他驻镇帮镇扶村","陆丰市甲东镇雨亭村七君子公园提升及配套建设工程","建设简易驿站，增加照明设备、休闲健身活动器材等基础设施","甲东镇雨亭村",145.47,"工程竣工验收合格率100%，受益群众满意度达95%以上。","甲东镇人民政府"]
[69,"金厢镇","2025年","其他驻镇帮镇扶村","2025年金厢镇海滨路应急抢险项目","完成挡土墙恢复,道路破除修复","金厢镇",245.47,"1、工程竣工验收合格率100%\n2、年度资金支出进度100%\n3、资金使用未发生重大违规违纪问题\n4、农户满意度≥90%\n5、项目建设进度达标率≥80%","金厢镇"]
[70,"金厢镇","2025年","典型村培育","2025年金厢镇大宫村路面修复项目","修复破顺路面并铺沥青1公里","金厢镇大宫村",30,"1、工程竣工验收合格率100%\n2、年度资金支出进度100%\n3、资金使用未发生重大违规违纪问题\n4、农户满意度≥90%\n5、项目建设进度达标率≥80%","金厢镇大宫村"]
[71,"金厢镇","2025年","其他驻镇帮镇扶村","2025年金厢镇文旅数字化建设项目","网站、app小程序、数字旅游地图、网络购票、数字导游等系统搭建运营","金厢镇",100,"\n1、年度资金支出进度100%\n2、资金使用未发生重大违规违纪问题\n3、农户满意度≥90%\n4、项目建设进度达标率≥80%","金厢镇"]
[72,"金厢镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市金厢镇山门村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","金厢镇山门村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","金厢镇山门村"]
[73,"内湖镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市内湖镇西陂村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","内湖镇西陂村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","内湖镇西陂村"]
[74,"内湖镇","2025年","典型村培育","内湖村吴爷公护河堤南侧硬底化工程","护河堤边小埕硬底化及村道塌陷修补面积3000平方米、村道塌陷100米长","内湖村",30,"年度资金支出进度100%\n工程竣工验收合格率100%\n群众参与乡村振兴率80%\n改善农村人居环境100%\n农户满意度100%","内湖镇人民政府"]
[75,"桥冲镇","2025年","其他驻镇帮镇扶村","陆丰市桥冲镇禾潭村前池塘建设项目","砼挡土墙130米，池塘清理淤泥，体积1200立方米，抽水体积600立方米，仿木护栏130米,道路硬底化面积200平方米","禾潭村",55,"1、年度建设项目开工率100%；2、年度建设任务完成率≥95%；3、受益群众满意度≥95%","桥冲镇人民政府"]
[76,"桥冲镇","2025年","典型村培育","陆丰市桥冲镇禾潭村五村和鲤鱼山道路硬底化项目","禾潭五村池塘至伯公路，约200米；禾潭鲤鱼山路，约50米","禾潭村",30,"1、年度建设项目开工率100%；2、年度建设任务完成率≥95%；3、受益群众满意度≥95%","桥冲镇人民政府"]
[77,"桥冲镇","2025年","典型村培育","陆丰市桥冲镇大塘村沙墩至明珠村及东湖路道路硬底化项目","沙墩至明珠村道路长178米，宽3.5米；东湖路道路总长181米，宽4米","大塘村",30,"1、年度建设项目开工率100%；2、年度建设任务完成率≥95%；3、受益群众满意度≥95%","桥冲镇人民政府"]
[78,"桥冲镇","2025年","其他驻镇帮镇扶村","陆丰市桥冲镇明珠村至大塘圩仔前路硬底化项目","总长667米，宽3.5米","大塘村",43,"1、年度建设项目开工率100%；2、年度建设任务完成率≥95%；3、受益群众满意度≥95%","桥冲镇人民政府"]
[79,"桥冲镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市桥冲镇下塘村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","桥冲镇下塘村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","桥冲镇下塘村"]
[80,"上英镇","2025年","其他驻镇帮镇扶村","上英镇新寮村农田水闸改造提升","北洋村民小组桥沟农田水闸、兰沟农田水闸改造提升","上英镇新寮村",50.47,"工程竣工验收合格率100%，农户满意度≥90%","陆丰市上英镇人民政府"]
[81,"上英镇","2025年","典型村培育","上英镇钱广村灌溉排水渠清淤整治项目","1.沟渠清淤:对农村排水沟渠进行主沟渠清淤，清除沟渠内的淤泥、垃圾、杂草等杂物，恢复沟渠的排水能力。\n2.沟渠疏通:对排水沟渠进行疏通，清除沟渠内的障碍物，确保排水畅通\n3.沟渠修复:对沟渠的破损部分进行修复，包括沟渠的加固、修补等。","上英镇钱广村",30,"工程竣工验收合格率100%，农户满意度≥90%","上英镇钱广村民委员会"]
[82,"上英镇","2025年","典型村培育","上英镇豪路村水利渠清淤项目","1.针对豪路村内5公里水利渠道清淤；\n2.沟渠修复:对沟渠的破损部分进行修复，包括沟渠的加固、修补等。","上英镇豪路村",30,"工程竣工验收合格率100%，农户满意度≥90%","上英镇豪路村民委员会"]
[83,"上英镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市上英镇英施村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","上英镇英施村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","上英镇英施村"]
[84,"上英镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市上英镇英郑村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","上英镇英郑村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","上英镇英郑村"]
[85,"潭西镇","2025年","典型村培育","崎头村口人居环境整治及绿化工程项目","崎头村路口标志石头周边环境整治及部分绿化","崎头村",30,"群众参与乡村振兴率≥80\n改善农村人居环境≥100%\n提升美丽乡村绿化美化","崎头村民委员会"]
[86,"潭西镇","2025年","典型村培育","新埔村新坣村绿美生态小公园提升项目","大仕大王庙侧边绿化及人行便道建设","新埔村",30,"打造美丽乡村生态小公园\n提升村民幸福感和满意度","新埔村民委员会"]
[87,"潭西镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市潭西镇潭西村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","潭西镇潭西村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","潭西镇潭西村"]
[88,"潭西镇","2025年","扶持壮大村集体经济","2025年汕尾市陆丰市潭西镇崔陂村扶持壮大村级集体经济项目","拟计划投入企业，以固定分红收益形式壮大村集体经济","潭西镇崔陂村",50,"扶持村集体经济发展的村数≥1个；村集体经济收入明显增加；基层党组织凝聚力有所增强；农民满意度≥90%；基层干部满意度≥90%。","潭西镇崔陂村"]
[89,"西南镇","2025年","典型村培育","西南镇青塘村委新建晒谷场建设项目","预计新建村民晒谷场2个，3000平方米","青塘村",30,"支持美丽乡村建设数量1个；工程竣工验收合格率100%，农户满意度≥90%","青塘村民委员会"]
[90,"西南镇","2025年","典型村培育","西南镇陂屯村委村内道路道路路灯安装项目","计划陂屯村全村道路路灯安装共计5km","陂屯村",30,"支持美丽乡村建设数量1个；工程竣工验收合格率100%，农户满意度≥90%","陂屯村民委员会"]
[91,"西南镇","2025年","其他驻镇帮镇扶村","西南镇深坑村委马路村至深坑村道路硬底化工程","计划对马路村至深坑村道路约2公里进行硬底化","深坑村",160,"支持美丽乡村建设数量1个；工程竣工验收合格率100%，农户满意度≥90%","深坑村民委员会"]
[92,"西南镇","2025年","其他驻镇帮镇扶村","西南镇西南村委步龙村至青塘村云前村道路硬底化工程","计划从青塘村云前村小组至西南村步龙村小组约3公里进行硬底化","西南村",240,"支持美丽乡村建设数量1个；工程竣工验收合格率100%，农户满意度≥90%","西南村民委员会"]
[93,"西南镇","2025年","其他驻镇帮镇扶村","西南镇西南村委南山村到深坑村硬底化工程","计划从西南村委南山到深坑村进行硬底化","西南村",50,"支持美丽乡村建设数量1个；工程竣工验收合格率100%，农户满意度≥90%","西南村民委员会"]
[94,"西南镇","2025年","典型村培育","西南镇青塘村委青塘大桥桥头公园建设工程","计划对青塘大桥旁建设一处桥头公园","青塘村",100,"支持美丽乡村建设数量1个；工程竣工验收合格率100%，农户满意度≥90%","青塘村民委员会"]
[95,"西南镇","2025年","其他驻镇帮镇扶村","西南镇屯埔村委屯埔河西边陇段灌溉蓄水陂头修复项目","计划拆除现状拦河坝及两岸挡墙，新建拦河坝、上游护底、陂身及消力池等","屯埔村",60,"支持美丽乡村建设数量1个；工程竣工验收合格率100%，农户满意度≥90%","屯埔村民委员会"]
[96,"西南镇","2025年","其他驻镇帮镇扶村","西南镇西山寨北门公园建设工程","计划以西山寨北门湖为核心，在湖周边设置石凳，并打造内湖景观，与古宅院结合，打造具有粤东风情特色的园林风光；为村民以及游客提供休闲、观赏及游览为主的公园。预计投入120万元；","西南村",120,"支持美丽乡村建设数量1个；工程竣工验收合格率100%，农户满意度≥90%","西南村民委员会"]
[97,"铜锣湖农场","2025年","典型村培育","麻竹坑村文化活动中心","1.建设占地面积70平方，设计两层\n2.外墙贴瓷砖，内墙刷墙面漆，贴地砖。\n3.配套一部电视、一台空调、乒乓球桌、棋牌桌等。","铜锣湖农场麻竹坑村",30,"该项目的建成将覆盖麻竹坑村农户538户，人口2668人，其中受益老龄人口650人左右，满足老年人的精神文化需求。\n\n","麻竹坑村委会"]